## Sheet1
CAPSTONE PROJECT PLANNING
25 Aug 2023 - 15 Sep 2023
| SUN | MON | TUE | WED | THU | FRI | SAT
[6 empty] | 25 | 26
[6 empty] | - Research CV use cases - Settle on 2 ideas | - Make slides - Search for data
| 27 | 28 | 29 | 30 | 31 | 1 | 2
| - Make slides - Try out simple classification mobilnet | - Try out the another transfer learning model - Take pics for test dataset - Read up on how other ppl dealt w poor scores for multiclass classi. | - Carry out EDA - Write out the problem statement etc properly - Try out the another transfer learning model | - Collect more test photos - Try data augmentation - Test model again - Recap NN - Test out Resnet | - Figure out how to pull up model scores - Try out additional hidden layer - Create working document to track model experiements | - Try alternative input pipeline - BUFFER DAY - PULL UP MODEL SCORE - Watch youtube videos (Localization / Detection) '- Target: explore object detection | - Explore object detection (MUST) - Labelling for localisation - Test out 1 model
| 3 | 4 | 5 | 6 | 7 | 8 | 9
| - Explore object detection (MUST) - Explored YOLOv5 | - Try out the YOLOv8 model - Read up abit on Func API | - Fix YOLOv8 code - Achieve video prediction output - create computer vision reading list | - Try Functional API? - Tidy up notebooks for pushing - Add on EDA - Gitpush progress | - Tidy up notebooks for pushing - Add on EDA - START DOING DEPLOYMENT | - Deployment - Continue refining notebook | - Complete deployment? - Prep slides? - Go back and do more EDA?
| 10 | 11 | 12 | 13 | 14 | 15
| - Beef up explanatory text throughout all notebooks - Explore Functional API | - Ppt slides - Watch videos CV | - Tie up ppt slides - Make script | CAPSTONE DRY RUN | - Rehearse - Medium article? | FINAL CAPSTONE
| PREP THINGS TO DO |  |  | AIMS
1 | Search for data |  | 1 | Create Classification model for alphabets
2 | List down some approaches - types of models |  | 2 | Do a single experiment as POC for part 2 - phrases
3 | Types of EDA I can do? |  | 3 | Deployment